## Sheet1
Task | Start Date | End Date | Duration
Investigation on the Existing Food Delivery Platform | 2023-10-16 | 2023-10-26 | 10
Comparison between food delivery platform | 2023-10-20 | 2023-10-28 | 8
Research on recommendation system | 2023-10-24 | 2023-10-29 | 5
Write Project proposal | 2023-10-25 | 2023-11-03 | 9
Research on CF and Content-based recommendation | 2023-10-29 | 2023-11-10 | 12 | 45217 | 45385
Project proposal | 2023-10-22 | 2023-11-03 | 12
Function requirements analysis | 2023-11-01 | 2023-11-18 | 17
System design (divided into several modules) | 2023-11-14 | 2023-11-30 | 16
Database design | 2023-11-20 | 2023-11-26 | 6
Web Implementation | 2023-12-01 | 2024-02-10 | 71
Progress report | 2023-12-10 | 2023-12-27 | 17
Recommend function design | 2024-01-02 | 2024-01-10 | 8
Develop recommend function | 2024-01-11 | 2024-03-01 | 50
Test and evaluate website function | 2024-02-10 | 2024-02-20 | 10
System testing & performance analysis | 2024-02-11 | 2024-02-21 | 10
Final report | 2024-02-09 | 2024-03-15 | 35
Create Poster | 2024-03-16 | 2024-04-15 | 30